## Variance Request Process
Variance Request Process
1 | Supt to Submit Flare Variance Form to AMPROE
2 | AMPROE to QC and input into tracking spreadsheet
3 | AMPROE to obtain needed signatures (AMPMGR / GMO)
4 | AMPROE to scan / save variance form to O: Drive (paper copy will not be kept)
5 | AMPROE will send out tracking spreadsheet to Supt's weekly (along with Weekly Report on Sunday)
6 | Supt to Update Column G in tracking spreadsheet weekly & take any action needed
O: Drive Folder
\\CABA0NTDFS1.CABA0.CHEVRONTEXACO.NET\SHARE\COPI\Malongo\Production\Prod. Mgr. Direct Reports- Confidential\AMPROE\Flare Variance

## Non-Routine
Flaring Variance Request |  |  |  | Variance Expired
Non-Routine |  |  |  | Variance to Expire within 28 days
Variance Ended
Supt Input Required Weekly
Area | Flare Point | Reason for Flare | Variance # | Flare Start Date | Original Expected Flare Duration (Days) | Variance End Date | Expected Flare End Date | Updated Expected Flare Duration | Status* (see note) | Reported By | Expected Flare Rate (mmcfd) | LPO (bopd) | AMPMGR Approval | GMO Approval
BBLT | HP & LP Flares | Water ingress into the annulus on the R-01 subsea riser prevents gas inj | 1 | 2011-01-01 | 365 | 2011-12-31 | 2011-12-31 | 365 | No Action Needed | Chuck Blevins | 2.5 | 5000 | 2011-04-16 | Needed
Area B | South Nemba Remote (HP) Flare | Gas compressors out of service due to May 2010 fire. Assuming Sept 1 start-up of compression at this facility. | 1 | 2011-01-01 | 243 | 2011-08-31 | 2011-08-31 | 243 | No Action Needed | Butch Tucker | 175 |  | 2011-04-08 | 2011-04-13
Malongo | KWIP Remote Flare | Compressor Train A Turbine Engine Failure and Change Out | 1 | 2011-04-16 | 21 | 2011-05-06 | 2011-05-08 | 23 | Variance Ended | Derrell Scott | 50 | 9285 | Needed | N/A
Area B | South Sanha Remote Flare | Mechanical Problems with the LP Compressor; unable to get engine to rotate. Suspect problem is with engine accessory drive; maintenance continues to troubleshoot. | 1 | 2011-04-16 | 28 | 2011-05-13 | 2011-05-13 | 28 | No Action Needed | Butch Tucker | 140 | 12000 | 2011-04-19 | N/A
Malongo | Delta Aux Remote Flare | Mainteance flaring while host compressor platform GIP Delta is down | 1 | 2011-04-17 | 19 | 2011-05-05 | 2011-05-08 | 22 | Variance Ended | Derrell Scott | 23.5 | 3042 | 2011-04-18 | N/A
2011-06-07
[5 empty] | Today's Date --> | 2011-05-10
*Flare can continue 48 hours past Variance end date without submitting updated variance request
Formulas:
Variance End Date = [Flare Start Date]+[Original Expected Flare Duration (Days)]-1
Variance End Date = [Variance End Date, row below]+28

## Routine
Flaring Variance Request | [5 empty] | 2011-06-07
Routine | [5 empty] | 2011-05-10 | <--Today's Date
Area | Flare Point | Reason for Flare | Variance # | Flare Start Date | Expected Flare Duration (Days) | Variance End Date | Reported By | Expected Flare Rate (mmcfd) | LPO (bopd) | AMPMGR Approval | GMO Approval
Malongo | GS Alfa | Low pressure gas source not collected | 1 | 2011-01-01 | 365 | 2011-12-31 | Derrell Scott | 7.8 | 1502 | 2011-04-21 | Needed
Malongo | GS Alfa | Low pressure gas source not collected | 1 | 2011-01-01 | 365 | 2011-12-31 | Derrell Scott | 2.5 | 1506 | 2011-04-21 | Needed
Malongo | KWIP remote flare | Flaring above gas train capability to gain oil production | 1 | 2011-01-01 | 365 | 2011-12-31 | Derrell Scott | 16.8 | 2245 | Needed | Needed
Malongo | GS Kilo Flare boom | Flare buing above gas train capability to gain oil production | 1 | 2011-01-01 | 365 | 2011-12-31 | Derrell Scott | 15.8 | 1447 | Needed | Needed
Takula | TGPP boom flare | Flaring above 2 MM due to systen stabibility | 1 | 2011-01-01 | 365 | 2011-12-31 | Gabriel Ivaba | 5 | 3000 | Needed | Needed
Sanha | HP Remote Flare and LP Boom Flare | Flaring above the capacity of reinjection units due to ambient and design conditions | 1 | 2011-01-01 | 365 | 2011-12-31 | Emanuel Dombolo | 30 |  | Needed | Needed
Area B | North Nemba Boom (LP) Flare | Flared gas is a result of vapors (light ends) flashed from the oil through the treating process. The planned South Nemba Auxillary facility (commission 2014) is being designed to capture these vapors. | 1 | 2011-01-01 | 365 | 2011-12-31 | Butch Tucker | 10 |  | 2011-04-08 | 2011-04-13
Area B | South Nemba Boom (LP) Flare | Flared gas is a result of vapors (light ends) flashed from the oil through the treating process. The planned South Nemba Auxillary facility (commission 2014) is being designed to capture these vapors. | 1 | 2011-01-01 | 365 | 2011-12-31 | Butch Tucker | 5 |  | 2011-04-08 | 2011-04-13
*Start date of 01-Jan-11 input for all routine flaring
Formulas:
Variance End Date = [Flare Start Date]+[Expected Flare Duration (Days)]-1

## 2011 Forecast_Letter
| 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Area | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2010 Average
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Malongo | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000
Area B | 196000 | 196000 | 196000 | 196000 | 196000 | 196000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 116350.6849
Sanha | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000 | 29000
GTA | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500
Terminal | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Block 0 | 309500 | 309500 | 309500 | 309500 | 309500 | 309500 | 151500 | 151500 | 151500 | 151500 | 151500 | 151500 | 229850.6849